## Gantt
| Aim 1 | Aim 2 | Aim 3 | Aim 4 | Aim 5 | Notes
Date | Adaptive Mantel Test for Penalized Inference | Multi-subject Dynamic Connectivity | Covariate Inference for Dynamic Connectivity | Bayesian Methods for Dynamic Connectivity | Software and Data Analysis
February (2018) | Submit methodology manuscript. | Begin project, extending CM Ting’s sf-VAR code for multiple subjects. |  |  | Update Adaptive Mantel Package.
March |  | Compile initial results. | Begin covariate inference methods for dynamic connectivity. | Present proposed model. | Initial development of multi-subject dynamic connectivity tools. | Advancement Exam: March 28th ENAR Presentation: March 26th
April | [5 empty] | UCI LearnMem Conf: April 18th - 22nd
May
June | Submit applied data analysis manuscript. |  |  |  | Adaptive Mantel package finalized.
July |  | Submit methodology manuscript. |  |  |  | JSM Presentation: July 30th
August |  |  |  | Begin model implementation and simulation study. | Begin package for Bayesian dynamic connectivity modeling.
September |  |  | Manuscript submission (methods and/or applied analysis). |  | Finalize package for sf-VAR multi-subject dynamic connectivity analysis.
October
November
December
January (2019) |  |  |  | Submit methodology manuscript. | Finalize package for Bayesian dynamic connectivity modeling.